## week1
Task | Anticipated length of time to complete | Actual time length to complete | Scheduled completion date | notes
Read Lecture notes | 0.013889 |  | 2014-05-16
Read Sections 1.1-1.9, | 0.055556 | 0.010417 | 2014-05-16
Read 2.1-2.9, 2.12 | 0.052083 | 0.013889 | 2014-05-17
Read Sections 4.1-4.5 | 0.03125 | 0.0041667 | 2014-05-17
Discussion question 1 | 0.14583 | 0.080556 | 2014-05-18
DQ1 response 1 | 0.010417 | 0.0069444
DQ1 response 2 | 0.010417 | 0.0069444
DQ1 response 3 | 0.010417 | 0.010417
DQ1 response 4 | 0.010417 | 0.0069444
DQ1 response 5 | 0.010417 | 0.0069444
Discussion question 2 | 0.14583 | 0.093056 | 2014-05-18
DQ2 response 1 | 0.010417 | 0:10
DQ2 response 2 | 0.010417 | 0:30
DQ2 response 3 | 0.010417 | 0.010417
DQ2 response 4 | 0.010417 | 0.010417
DQ2 response 5 | 0.010417 | 0.010417
Hand-in assignment | 0.16667 | 0.25 | 2014-05-21
Total | 0.71528 | 0.54931
Formulas:
Anticipated length of time to complete = SUM(B2:[Anticipated length of time to complete, row above])
Actual time length to complete = SUM(C2:[Actual time length to complete, row above])

## week2
Task | Anticipated length of time to complete | Actual time length to complete | Scheduled completion date | notes
Discussion question 1 | 0.14583 | 0.11806 | 2014-05-24
Discussion question 2 | 0.14583 | 0.052083 | 2014-05-25
Read Lecture notes | 0.013889 |  | 2014-05-26
Read Sections 2.10-2.11 | 0.010417 |  | 2014-05-26
Read Sections 4.8-4.12 | 0.034722 |  | 2014-05-26
Read Sections Sections 5.1-5.5 | 0.017361 |  | 2014-05-26
DQ1 response 1 | 0.010417 |  | 2014-05-25
DQ1 response 2 | 0.010417 |  | 2014-05-26
DQ1 response 3 | 0.010417 |  | 2014-05-26
DQ1 response 4 | 0.010417 |  | 2014-05-27
DQ1 response 5 | 0.010417 |  | 2014-05-28
DQ2 response 1 | 0.010417 |  | 2014-05-25
DQ2 response 2 | 0.010417 |  | 2014-05-26
DQ2 response 3 | 0.010417 |  | 2014-05-26
DQ2 response 4 | 0.010417 |  | 2014-05-27
DQ2 response 5 | 0.010417 |  | 2014-05-28
Hand-in assignment | 0.16667 |  | 2014-05-28
Total | 0.63889 | 0.17014
Formulas:
Anticipated length of time to complete = SUM(B2:[Anticipated length of time to complete, row above])
Actual time length to complete = SUM(C2:[Actual time length to complete, row above])